# UDAQ Approval Order Timeline

Overall timeline for AO issuance after submittal to UDAQ is typically 6-12 months depending on project complexity, and may be as fast as 3 months for simple projects submitted to efficient permit engineers. Projects near or above major NSR thresholds should plan on 12-18 months of processing by UDAQ.

| Step description | Duration (rule citation) | Typical duration |
| --- | --- | --- |
| Source prepares Notice of Intent | N/A | 2-4 months depending on project complexity |
| Submit Notice of Intent (NOI) to UDAQ | N/A (administrative start point) |  |
| UDAQ completeness review and notify applicant whether the application is complete. | 30 days (UAC R307-401-5) | 30-45 days |
| UDAQ draft engineering review | N/A | 1-8 months depending on project complexity |
| UDAQ internal review | N/A | 2 weeks |
| Source review and revisions | 10 business days requested, extended upon request | 2-4 weeks depending on the number of comments |
| Public comment period (when required) | 30 days (UAC R307-401-7) |  |
| Request extension of the public comment period (if requested/approved). | Up to 30 additional days; request within 15 days of notice publication (UAC R307-401-7) |  |
| Request a public hearing on the proposed approval/disapproval order. | Request within 15 days of notice publication (UAC R307-401-7) |  |
| Hold public hearing (if granted). | N/A |  |
| Respond to comments and issue approval order (AO) | N/A | Variable depending on comments received (2+ weeks) |

Note: issuance of an approval order is required 90 days after a complete application is received (+ up to three 30-day extensions) (UAC R307-401-5).